## Slide 1: Herding Cats
Project and Task Management Techniques for Student Affairs
Sarah Rocker and Kitty Jones, Summer 2011
Notes: <number>
Kitty's intro about usefulness of these analytic tools for touchy feely oriented.
Introductions and Expecations.
Review of Format of the day. Say that we’ll be using an example project through this presentation and then break into groups to use their own examples.
How we hope this is relevant to people in all kinds of roles.

## Slide 2
Notes: <number>

## Slide 3: Project Management
A systematic process used to initiate, plan, execute and evaluate projects in order to meet defined objectives.
Part Science
- in the systematic process and tools
Part Art
- in how one executes tasks and works with other people
- Author Rita Mulcahy, 2006
Notes: <number>

## Slide 4: Project Management Objectives:
Define the project
Reduce project to a set of manageable tasks
Obtain appropriate and necessary resources
Build a team or teams to perform the work
Plan and allocate resources to tasks
Monitor and manage the work
Report progress to co-workers, supervisor, or project team mates
Close down project when completed
Review and evaluate for lessons learned
Notes: <number>

## Slide 5: What is a Project?
A project has:
A beginning and an end
A defined purpose with a product or deliverables
Requires resources such as time and funding
Elements of uncertainty (risk)
Notes: <number>
Ask for attributes of project

## Slide 6: Examples of Projects
The development and introduction of new services
Creating improvements to an existing process
The production of a newsletter or website
Others?
Notes: <number>

## Slide 7: How is a project different than other work?
A continuous process is not a project. The development of a new policy is a project, but the day to day operation of that policy is not.
Continuous processes are usually managed by individuals or departments, not project managers or project team.
Notes: <number>
So in student affairs, where most of our work is continual processes, we'll highlight at the end how we can use these techniques.

## Slide 8: How is Project Management Relevant to Student Affairs?
Techniques from PM are most relevant for those who have a specific job or project that includes the following:
A defined goal
Time, cost and quality constraints
Requires expertise and support from other areas
Involves a unique scope of work
Notes: <number>

## Slide 9: Project Management Methodology
Project Phases for Student Affairs:
1. Conceptualization
2. Planning and Preparation
3. Implementation
4. Assessment
http://www.mittechnical.com
Notes: <number>
Ask for an example project in student affairs and go through the steps.
PM Institute
Rational Unified Processes – IBM Prince 2 used in the UK

## Slide 10: Project Phases in Student Affairs
Conceptualization – identifying the need for and scope of the project.
Planning and Preparation – involves creating the project outline, addressing feasibility and procuring resources and identifying team members and stakeholders
Implementation – is the execution of the project. Observe progress and respond to changes as they occur
Assessment – Close the project, review what worked and what didn’t. Note learnings and changes for the future. Share information with others.
Notes: <number>
Take time to talk about each phase.
Kitty will lead folks through envisioning what the phases of a hiring project would like.

## Slide 11: Roles of a Project Manager
Gains approval for the project aim
Selects and leads the team and setting individual objectives
Ensures a feasibility study is complete
Ensures that the project is planned in appropriate detail
Allocates and monitors the work and cost
Motivates the team
Reports progress back to the team or organization
Helps the team to solve problems that may arise in the project
Ensures that the team is successful in attaining it’s goal
Closes down and reviews the project
Notes: <number>
For someone whose title is Project Manager, these are the typical responsibilities:
Think about who does these things in your department, etc. Which do you do? Are there any being missed?
Different sized project require varying degrees of management. For example, how in depth a feasibility study is, depends on the scope of the project and the resources needed. Feasibility might be something as simple as: Is i within our budget and timeline to revamp our website?

## Slide 12: Tools and Techniques
Objective Setting
This ensures that the project objectives can be measured and verified
Brain Storming
Technique used at all stages, which encourages creative thinking and problem solving
Work Breakdown Structures
Involves identifying key elements and breaking them down in to component parts until all manageable work packages/tasks have been identified. Once these have been identified they can be allocated to individual team members.
Gantt Charts
Are used to show the schedule and sequencing of a projects. They include start and finish dates for specific tasks or milestones within a project.
Notes: <number>
You may already be doing some or all of these. Most of us have experience with the first two, especially.
What does brainstorming and objective setting look like in your department? How does this take place? If it doesn't take place, when could it? In a staff meeting? 1 on 1 with supervisor?
Workbreakdown Structures:
You may know these as flow chart, mind maps, graphs.
They can take shape either as a visual form or in an outline form.
Gantt Charts:
Can be used for components of the tasks on a WBS. Can also help to identify milestones for assessment.

## Slide 13: Work Breakdown Structure
Hiring new staff
The Position
1.1
The Candidates
1.2
The Process
1.3
Authorization
to hire
1.1.1
Job
Description
1.1.2
Search
Committee
1.1.3
Getting HR’s OK
to proceed
1.1.4
Recruiting
1.2.1
Create
Announcement
1.2.1.1
Post
Announcement
1.2.1.2
Evaluating
1.2.2
Determine essential
vs. desirable criteria
1.2.2.1
Create interview
questions
1.2.2.2
Interviews
1.3.1
Selection and
Closure
1.3.2
Schedule with
Committee
1.3.1.1
Schedule with
Candidates
1.3.1.2
Assess diversity
and depth of pool
1.2.2.3
Committee makes
Recommendation
1.3.2.1
HR approval
1.3.2.2
Hiring authority
makes offer
1.3.2.3
Screen applications,
create shortlist
1.2.2.4
Conduct
Interviews
1.3.1.3
Notes: <number>

## Slide 14: The Element of Time: Gantt Charts
Microsoft Excel
Microsoft Outlook
Notes: <number>
The first known tool of this type was reportedly developed in 1896 by Karol Adamiecki, who called it a harmonogram. Adamiecki did not publish his chart until 1931, however, and then only in Polish. The chart is named after Henry Gantt (1861–1919), who designed his chart around the years 1910–1915.[1][2] (Wikipedia)

## Slide 15: Group Project
The overall aim and scope of the project and the benefit of doing it
Key objectives (include specific deliverables)
Resources available vs. needed
Key people (team, stakeholders, etc.)
Timeline and Milestones
Choose a project that you or someone in your group is planning. Identify the following elements and create a work breakdown structure for that project.
Notes: <number>

## Slide 16: Group Report Back
Which parts of the process were the most beneficial? The most challenging?
Were there any aspects of your project/department don’t jive with this model?

## Slide 17: Processes vs. Projects
Tools and techniques useful in both: objective setting, brainstorming, Work Breakdown Structure
Key elements to periodically review:
  Scope (any “scope creep”?)
  Resources (looking ahead for changes in needs or availability)
  People (do we have the right mix of people on our team? Any changes in stakeholders? Are we communicating effectively with both groups?)
  Assessment (are we regularly checking to make sure our activities are moving us toward our goals?)

## Slide 18: Resources
Creating Gantt Charts in Excel:
Video: http://www.youtube.com/watch?v=CW_wGSFavTc
Article: http://office.microsoft.com/en-us/excel-help/create-a-gantt-chart-in-excel-HA001034605.aspx
Template: http://office.microsoft.com/en-us/templates/excel-gantt-chart-TC030000350.aspx
Work Breakdown Structure Programs and Resources:
http://freemind.sourceforge.net/wiki/index.php/Main_Page
http://www.mind42.com/